## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Initial setup and navbar | 3 | 2023-08-10 | Initial setup and navbar implemented
Us2 : HouseList | 3 | 2023-08-11 | Implemented basic functionality for the list
Us3 : Searching | 5 | 2023-08-11 | Implemented basic functionality
Us4 : Sorting | 2 | 2023-08-11 | Implemented basic functionality and bonus
Us5: House details, recommended houses | 5 | 2023-08-16 | Implemented basic functionality, had struggle to find a way implement personal listing
Us6, Us7, Us8: Create Listing, edit listing. | 6 | 2023-08-17 | Implemented basic functionality. validation error functionality missing yet.
Us9: Modal window | 2 | 2023-08-17 | Implemented basic functionality
Responsive Design and About Page | 2 | 2023-08-18 | Everything is responsive
Code review | 2 | 2023-08-18 | Fixing bugs, trying to make things better
Bonus: About Page | 2 | 2023-08-17 | Implemented basic functionality | x
Bonus: Recommended Listings | 5 | 2023-08-15 | Implemented basic functionality | x
Bonus: Sorting methods | 3 | 2023-08-11 | Implemented Ascending and Descending filter methods | x
Total amount of hours | 30